## Start Here
CDC Recovery POC Evaluation Worksheet
Use this workbook to define realistic recovery tests, capture evidence, compare demonstrated behavior, and document the final decision.
How to Use This Workbook
1. Define the environment | Complete the Environment sheet before testing so every result is tied to a specific source, target, topology, workload, retention policy, and recovery objective.
2. Set the test plan | Review the eight recommended POC scenarios. Tailor the conditions without removing tests simply because a vendor does not normally demonstrate them.
3. Capture evidence | Record observable behavior, screenshots or artifact references, results, limitations, and open questions in the Evidence Log.
4. Rate capabilities | Use Demonstrated, Partially demonstrated, Not demonstrated, or Not applicable. Add evidence, not just a rating.
5. Compare vendors | Use one copy of the Vendor Comparison sheet or add vendor columns. Compare only like-for-like configurations and tests.
6. Document the decision | Summarize strengths, risks, dependencies, unresolved questions, and required follow-up in Decision Summary.
Rating Definitions
Demonstrated | The behavior was observed in the tested configuration and supported by retained evidence.
Partially demonstrated | Some behavior was observed, but scope, evidence, configuration, or limitations remain unresolved.
Not demonstrated | The capability was not shown, the evidence was insufficient, or the result did not meet the test objective.
Not applicable | The capability does not apply to the tested configuration. Explain why.
Final Evaluation Question
Could our normal operating team use the evidence demonstrated here to understand the failure, manage recovery, and defend the all-clear without depending entirely on the vendor or one internal specialist?
Note on I1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: One tiny thing I wonder about in the Evidence Log: should we add a “What this test established” field right before “Limitations / Remaining Uncertainty”? The whole POC article keeps coming back to don’t just say the test passed — say what the evidence actually proves and what it doesn’t. Feels like this would make that really explicit in the actual tool.

## Environment
POC Environment Definition
Complete before testing. Blue-font cells are inputs; gray text provides guidance.
Category | Field | POC Input | Guidance
POC | Environment/Configuration ID |  | Assign a unique ID to the exact source, target, topology, version, workload, retention model, and configuration tested.
POC | Vendor / platform |  | Name and edition being evaluated
POC | POC owner |  | Internal owner
POC | Vendor technical owner |  | Primary vendor contact
POC | Test dates |  | Use a specific date range
Source | Source technology and version |  | Example: Db2 for z/OS, Oracle, IMS, Kafka
Source | Capture method |  | Log-based, trigger-based, journal-based, other
Source | Normal transaction rate |  | Include units
Source | Peak transaction rate |  | Include units
Source | Source-history retention |  | Active, archived, journal, or other retained history
Source | Retention owner |  | DBA, storage, operations, other
Target | Target technology and version |  | Database, warehouse, lakehouse, application, other
Target | Apply method / configuration |  | Include transaction and commit behavior if known
Target | Target latency constraints |  | Expected normal operating range
Target | Direct writes allowed? |  | Yes / No / Conditional
Architecture | Topology |  | One-to-one, fan-out, consolidation, bidirectional, other
Architecture | Network assumptions |  | Bandwidth, latency, interruption scenarios
Architecture | Transformation rules |  | Filtering, mapping, enrichment, schema changes
Architecture | Downstream consumers |  | Applications, reports, APIs, analytics, workflows
Recovery | Recovery objective |  | RTO, acceptable lag, or business tolerance
Recovery | Reload / resync constraints |  | When is broader resynchronization unacceptable?
Recovery | Ordering requirements |  | Identify workloads where sequence matters
Recovery | Replay-sensitive consumers |  | Payments, notifications, inventory, workflows, other
Recovery | Validation requirements |  | Technical, business, audit, or regulatory evidence needed
Scope | Explicitly in scope |  | Sources, targets, workloads, tests
Scope | Explicitly out of scope |  | Document exclusions to prevent assumed coverage

## Test Plan
CDC Recovery POC Test Plan
Tailor the conditions to the production environment. Retain evidence for every result.
ID | POC Test | Purpose | Conditions to Introduce | Ask the Vendor to Demonstrate | Evidence to Retain | Primary Capabilities | Planned?
1 | Make replication fall behind | Distinguish running, lagging, progressing catch-up, and worsening backlog. | Create controlled load or target constraint so replication remains active but cannot keep pace. | Lag magnitude; backlog size and direction; capture vs. apply delay where available; throughput; processing-position advancement; source-history exposure. | Screenshots/exports of status, lag, backlog trend, throughput, positions, warnings, timestamps. | Catch-Up Visibility | Yes
2 | Stop replication during active processing | Inspect restart state and understand where processing resumes. | Introduce a safe, supported interruption during active transactions. Include an abrupt condition if supported. | Retained restart/process state; meaning of each marker; transaction boundary; retry/reprocessing behavior; inspectability before restart. | State before failure, state after failure, restart markers, logs, transaction IDs, resumed position. | Recovery-State Visibility | Yes
3 | Test historical recovery support | Establish dependencies on active, archived, journal, or other retained source history. | Make required changes older than the normal active-history window or emulate retrieval of retained history. | Required history; location; retention owner; retrieval path; manual steps; supported boundary; behavior when history is unavailable. | History references, retrieval times, configuration, processing start/end positions, vendor documentation. | Historical Recovery Support | Yes
4 | Create a stalled catch-up | Determine whether operators can distinguish catch-up activity from actual progress. | Begin catch-up, then constrain source, network, apply, or target conditions so the gap holds or grows. | Backlog direction; current rates; position advancement; retries/throttling; source/target effect; completion estimate basis. | Trend views, rates, positions, errors, timestamps, completion estimate assumptions. | Catch-Up Visibility | Yes
5 | Preserve and investigate failure evidence | Assess whether diagnostics support root-cause investigation and incident review. | Trigger a representative source, network, replication, or target failure. | Errors; surrounding activity; correlated lag/throughput; source/target context; retention; export; evidence available before and after restart. | Logs, traces, alerts, diagnostic exports, timeline, retention settings. | Diagnostics and Root-Cause Investigation | Yes
6 | Validate the recovered target | Determine what the platform can prove after recovery and what remains outside its scope. | Seed known discrepancies where practical: missing insert/update, unexpected record, duplicate, missing delete, stale value, transformation or ordering issue. | Comparison scope; supported sources/targets; compared keys/values; discrepancy detail; incident-window scoping; limits; additional validation required. | Seed list, source/target snapshots, comparison output, discrepancy findings, remediation, final evidence. | Validation Support | Yes
7 | Test replay and downstream-consumer impact | Make replay visible and assess coordination needs for non-idempotent consumers. | Accumulate changes during interruption and process them during catch-up. Include replay-sensitive event types if safe. | Replay window, types, volume, rate, retry behavior, duplicate protections, ordering, retained evidence. | Replay metrics, event examples, consumer observations, suppression/dedup steps, timing. | Replay and Idempotency Awareness | Yes
8 | Demonstrate the recovery boundary | Identify when restart/catch-up no longer applies and resynchronization or reload is required. | Test or walk through scenarios with unavailable state/history, inconsistent target, unsupported change, or broad discrepancy. | Supported restart cases; historical catch-up; targeted vs. broader resync; reload conditions; environment dependencies; operator evidence that the boundary is crossed. | Scenario matrix, limitations, decision criteria, required actions, documentation references. | All capability areas | Yes

## Environment_Config ID
POC Evidence Log
One row per test execution. Add rows as needed. Link or reference retained evidence.
Test ID | Vendor | Execution Date | Configuration ID | Failure / Condition Introduced | What Operators Could See | Restart / Processing State | Catch-Up / Replay Behavior | Validation Result | What This Test Established | Limitations / Remaining Uncertainty | Overall Rating | Evidence Link or File | Vendor Follow-Up | Owner / Due Date

## Capability Summary
Capability Evaluation Summary
Summarize demonstrated behavior for the exact configuration tested.
Capability | Rating | Evidence Log Test IDs | Configuration(s) | Evidence-Based Summary | Open Questions / Dependencies
Recovery-State Visibility
Historical Recovery Support
Catch-Up Visibility
Validation Support
Diagnostics and Root-Cause Investigation
Replay and Idempotency Awareness
Recovery Limits and Resynchronization Boundaries
Capability Interpretation
A capability should not be rated Demonstrated based only on product documentation or verbal explanation. The rating should reflect observable behavior and retained evidence from the tested source, target, topology, version, configuration, and failure scenario.

## Vendor Comparison
Vendor Comparison
Compare only tests conducted under equivalent conditions. Expand with additional vendor columns if needed.
Capability / Test | Vendor A | Vendor B | Vendor C | Comparison Notes
Environment/Confuration ID
Tested Configuration / Environment ID
Test Dates
Recovery-State Visibility
Historical Recovery Support
Catch-Up Visibility
Validation Support
Diagnostics and Root-Cause Investigation
Replay and Idempotency Awareness
Recovery Limits and Resynchronization Boundaries
Test 1: Lag and backlog
Test 2: Active-processing interruption
Test 3: Historical recovery
Test 4: Stalled catch-up
Test 5: Diagnostics
Test 6: Target validation
Test 7: Replay impact
Test 8: Recovery boundary
Overall confidence
Comparison Guardrail
Do not convert ratings into a single numeric score without preserving the evidence and conditions behind them. A capability demonstrated for one source, target, or topology should not be assumed to apply to another.
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I love the guardrail about only comparing like-for-like tests. Should we add a Tested Configuration / Environment ID row at the top of Vendor Comparison so whoever reads this later can immediately see which environment each vendor result came from? Feels especially important since so much of the whole framework says a result for one source/target/topology shouldn’t automatically be generalized to another.

## Decision Summary
POC Decision Summary
Use evidence, limitations, and configuration dependencies to support the decision.
Decision Area | Summary | Owner / Status
POC objective | What recovery questions did this POC need to answer?
Environment tested | Source, target, topology, version, workload, and retention model.
Overall recovery confidence | High / Moderate / Low, with evidence-based rationale.
Demonstrated strengths | Which capabilities were clearly demonstrated?
Partially demonstrated areas | What remains conditional, incomplete, or configuration-dependent?
Not demonstrated | Which claims were not established?
Recovery boundaries | When are targeted resync, broader resync, or reload required?
Operational readiness impact | Could normal operators manage recovery without vendor or specialist dependency?
Key risks | What could materially affect recovery, data integrity, or downstream operations?
Required follow-up | Additional tests, documentation, architecture review, or contractual clarification.
Decision recommendation | Proceed / Proceed with conditions / Additional evaluation / Do not proceed.
Decision rationale | Concise rationale tied to observed evidence.
Final Decision Question
Could our normal operating team use the evidence demonstrated here to understand the failure, manage recovery, and defend the all-clear without depending entirely on the vendor or one internal specialist?